## Sheet1
SL | API | Required Days | Estimated Date | Status | Comment | Date
1 | Employee Add | 1 |  | API READY | need to deploy | 2024-06-30
2 | Employee List | 1 |  | API READY | need to deploy | 2024-06-30
3 | Employee Edit | 1 |  | API READY | need to deploy | 2024-06-30
4 | Employee Delete | 1 |  | API READY | need to deploy | 2024-06-30
5 | User Create | 1 |  | API READY | need to deploy | 2024-06-30
6 | User List | 1 |  | API READY | need to deploy | 2024-07-01
7 | User Edit | 1 |  | API READY | need to deploy | 2024-07-01
8 | User Delete | 1 |  | API READY | need to deploy | 2024-07-01
9 | Login | 1 |  | API READY | no jwt | 2024-07-02
10 | Logout | 1 |  | API READY | no jwt | 2024-07-02
11 | Bazaar Item Add | 1 |  | API READY | need to deploy | 2024-07-02
12 | Bazaar Item List | 1 |  | API READY | need to deploy | 2024-07-02
13 | Bazaar Item Edit | 1 |  | API READY | need to deploy | 2024-07-02
14 | Bazaar Item Delete | 1 |  | API READY | need to deploy | 2024-07-02
15 | Bazaar Input | 1 |  | Pending
16 | Bazaar List | 1 |  | Pending
17 | Bazaar Edit | 1 |  | Pending
18 | Bazaar Delete | 1 |  | Pending
19 | Bazaar Approve | 1 |  | Pending
20 | Date Wise Bazaar Report | 1 |  | Pending
21 | Single Item Menu Create | 1 |  | API READY | need to deploy | 2024-07-05
22 | Single Item Menu List | 1 |  | API READY | need to deploy | 2024-07-05
23 | Single Item Menu Edit | 1 |  | API READY | need to deploy | 2024-07-05
24 | Single Item Menu Delete | 1 |  | API READY | need to deploy | 2024-07-05
26 | Multiple Item Menu Create | 1 |  | Pending
27 | Multiple Item Menu List | 1 |  | Pending
28 | Multiple Item Menu Edit | 1 |  | Pending
29 | Multiple Item Menu Delete | 1 |  | Pending
30 | Multiple Item Menu Approve | 1 |  | Pending
31 | Daily Cost Sector Add | 1 |  | API READY | need to deploy | 2024-07-06
32 | Daily Cost Sector List | 1 |  | API READY | need to deploy | 2024-07-06
33 | Daily Cost Sector Edit | 1 |  | API READY | need to deploy | 2024-07-06
34 | Daily Cost Sector Delete | 1 |  | API READY | need to deploy | 2024-07-06
35 | Daily Cost Add | 1 |  | Pending
36 | Daily Cost List | 1 |  | Pending
37 | Daily Cost Edit | 1 |  | Pending
38 | Daily Cost Delete | 1 |  | Pending
39 | Bill Create | 1 |  | Pending
40 | Bill List | 1 |  | Pending
41 | Bill Edit | 1 |  | Pending
42 | Bill Delete | 1 |  | Pending
43 | Bill Approval | 1 |  | Pending | Once a day or one by one ??
44 | Salary Payment Add | 3 |  | Pending
45 | Salary Payment List | 1 |  | Pending
46 | Salary Payment Edit | 3 |  | Pending
47 | Salary Payment Delete | 1 |  | Pending
48 | Date Wise Income Report | 1 |  | Pending
49 | Date Wise Expense Report | 1 |  | Pending
50 | Date Wise Income-Expense Report | 1 |  | Pending
51 | Date Wise Loss & Profit | 1 |  | Pending
52 | Date Wise Bill Report | 1 |  | Pending
53 | Date Wise Total Collection by All Payment Method | 1 |  | Pending
54 | Date Wise Total Collection by Specific Payment Method | 1 |  | Pending
55 | Sharholders % | 1 |  | Pending | Need to discuss
56 | Employee By Id | 1 |  | API READY | need to deploy | 2024-07-01
57 | User By Id | 1 |  | API READY | need to deploy | 2024-07-01
58 | Bazaar Item By Id | 1 |  | API READY | need to deploy | 2024-07-02
59 | Single Item By Id | 1 |  | API READY | need to deploy | 2024-07-05
60 | Daily Cost Sector By Id | 1 |  | API READY | need to deploy | 2024-07-06
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100